## Project Management Data
Excel Sample Data
Project Management Data
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0%
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0%
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30%
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0%
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%

## Working Sheet
Project Name | Task Name | Assigned to | Start Date | Days Required | Day Required Brackets | End Date | Progress | Progress Brackets
Marketing | Market Research | Alice | 2024-01-01 | 13 | Short Day Required | 2024-01-14 | 78% | High Progress
Marketing | Content Creation | Bob | 2024-01-14 | 14 | Short Day Required | 2024-01-28 | 100% | Almost Done
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | Medium Day Required | 2024-02-19 | 45% | Medium Progress
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | Medium Day Required | 2024-03-14 | 0% | Low Progress
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | Short Day Required | 2024-01-20 | 100% | Almost Done
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | Short Day Required | 2024-01-30 | 78% | High Progress
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | Medium Day Required | 2024-02-29 | 0% | Low Progress
Customer Service | Service Improvement | Hannah | 2024-02-01 | 22 | Medium Day Required | 2024-02-23 | 100% | Almost Done
Customer Service | Ticket Resolution | Ian | 2024-02-24 | 25 | Medium Day Required | 2024-03-20 | 100% | Almost Done
Customer Service | Customer Feedback | Julia | 2024-03-21 | 30 | Medium Day Required | 2024-04-20 | 0% | Low Progress
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | Medium Day Required | 2024-02-24 | 10% | Low Progress
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | Medium Day Required | 2024-02-09 | 78% | High Progress
Financial | Investment Planning | Mark | 2024-03-19 | 25 | Medium Day Required | 2024-04-13 | 100% | Almost Done
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | Medium Day Required | 2024-01-25 | 50% | Medium Progress
Research | Data Collection | Olivia | 2024-01-26 | 32 | Medium Day Required | 2024-02-27 | 0% | Low Progress
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | Medium Day Required | 2024-03-26 | 0% | Low Progress
Development | Software Development | Quinn | 2024-01-02 | 36 | Medium Day Required | 2024-02-07 | 100% | Almost Done
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | Medium Day Required | 2024-03-13 | 0% | Low Progress
Development | Code Review | Sam | 2024-03-14 | 30 | Medium Day Required | 2024-04-13 | 0% | Low Progress
Production | Manufacturing | Tim | 2024-01-03 | 47 | Long Day Required | 2024-02-19 | 30% | Low Progress
Production | Quality Control | Ursula | 2024-02-17 | 27 | Medium Day Required | 2024-03-15 | 0% | Low Progress
Production | Packaging Design | Victor | 2024-03-14 | 22 | Medium Day Required | 2024-04-05 | 0% | Low Progress
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | Long Day Required | 2024-03-03 | 70% | High Progress
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | Short Day Required | 2024-01-26 | 78% | High Progress
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | Medium Day Required | 2024-03-09 | 0% | Low Progress
Support | Technical Support | Zoe | 2024-01-01 | 25 | Medium Day Required | 2024-01-26 | 100% | Almost Done
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | Medium Day Required | 2024-02-27 | 100% | Almost Done
Support | Software Updates | Bella | 2024-03-02 | 22 | Medium Day Required | 2024-03-24 | 0% | Low Progress
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | Medium Day Required | 2024-02-02 | 40% | Medium Progress
Operations | Inventory Management | Diane | 2024-02-03 | 25 | Medium Day Required | 2024-02-28 | 0% | Low Progress
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | Short Day Required | 2024-03-20 | 0% | Low Progress
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | Medium Day Required | 2024-02-06 | 60% | Medium Progress
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | Medium Day Required | 2024-03-05 | 0% | Low Progress
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | Medium Day Required | 2024-03-31 | 0% | Low Progress
Training | Employee Training | Isaac | 2024-01-04 | 27 | Medium Day Required | 2024-01-31 | 80% | High Progress
Training | Certification Programs | Jane | 2024-01-28 | 30 | Medium Day Required | 2024-02-27 | 0% | Low Progress
Training | Skill Development | Kyle | 2024-02-28 | 22 | Medium Day Required | 2024-03-21 | 0% | Low Progress
Events | Event Planning | Laura | 2024-01-03 | 25 | Medium Day Required | 2024-01-28 | 30% | Low Progress
Events | Conference Management | Mike | 2024-02-03 | 20 | Short Day Required | 2024-02-23 | 0% | Low Progress
Events | Sponsorship Coordinatio | Nancy | 2024-02-24 | 35 | Medium Day Required | 2024-03-30 | 0% | Low Progress
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | Medium Day Required | 2024-01-28 | 50% | Medium Progress
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | Medium Day Required | 2024-02-28 | 100% | Almost Done
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | Short Day Required | 2024-04-18 | 0% | Low Progress
Engineering | Product Design | Rachel | 2024-01-02 | 25 | Medium Day Required | 2024-01-27 | 20% | Low Progress
Engineering | System Integration | Sam | 2024-02-02 | 22 | Medium Day Required | 2024-02-24 | 0% | Low Progress
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | Medium Day Required | 2024-03-21 | 0% | Low Progress

## Pivot Table
Row Labels | Count of Assigned to
Consulting | 3
Customer Service | 3
Development | 3
Engineering | 3
Events | 3
Financial | 3
Logistics | 3
Marketing | 4
Operations | 3
Product Dev | 3
Production | 3
Research | 3
Sales | 3
Support | 3
Training | 3
Grand Total | 46
Row Labels | Average of Progress
Consulting | 20%
Customer Service | 66.67%
Development | 33.33%
Engineering | 6.667%
Events | 10%
Financial | 62.67%
Logistics | 50%
Marketing | 55.75%
Operations | 13.33%
Product Dev | 59.33%
Production | 10%
Research | 16.67%
Sales | 49.33%
Support | 66.67%
Training | 26.67%
Grand Total | 36.89%
Row Labels | Count of Progress Brackets
Almost Done | 9
High Progress | 6
Low Progress | 26
Medium Progress | 5
Grand Total | 46
Row Labels | Count of Assigned to
Long Day Required | 2
Medium Day Required | 36
Short Day Required | 8
Grand Total | 46

## Dashboard
Dashboard Project Management
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.